## Prob. 12.1b
SLASH BURNING EARLIEST START AND FINISH
Arc
Activity | Expected duration | Earliest start ES | Earliest finish EF | From activity | EF | To activity | ES
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 5 | 0 | 5 | Start | 0 | B | 0
B | 10 | 0 | 10 | Start | 0 | C | 0
C | 4 | 0 | 4 | Start | 0 | D | 0
D | 2 | 0 | 2 | A | 5 | E | 5
E | 2 | 5 | 7 | A | 5 | F | 10
F | 3 | 10 | 13 | B | 10 | F | 10
End | 0 | 13 | 13 | C | 4 | End | 13
| Total | 28 |  | D | 2 | End | 13
| (min) |  |  | E | 7 | End | 13
|  |  |  | F | 13 | End | 13
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.2b
SLASH BURNING LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | 4 | 4 | Start | 4 | A | 7
A | 5 | 7 | 12 | Start | 4 | B | 4
B | 8 | 4 | 12 | Start | 4 | C | 11
C | 4 | 11 | 15 | Start | 4 | D | 13
D | 2 | 13 | 15 | A | 12 | E | 13
E | 2 | 13 | 15 | A | 12 | F | 12
F | 3 | 12 | 15 | B | 12 | F | 12
End | 0 | 15 | 15 | C | 15 | End | 15
| Total | 52 |  | D | 15 | End | 15
| (max) |  |  | E | 15 | End | 15
| Project earliest finish: |  | 15 | F | 15 | End | 15
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.2c
SLASH BURNING LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | -1 | -1 | Start | -1 | A | 2
A | 5 | 2 | 7 | Start | -1 | B | -1
B | 8 | -1 | 7 | Start | -1 | C | 6
C | 4 | 6 | 10 | Start | -1 | D | 8
D | 2 | 8 | 10 | A | 7 | E | 8
E | 2 | 8 | 10 | A | 7 | F | 7
F | 3 | 7 | 10 | B | 7 | F | 7
End | 0 | 10 | 10 | C | 10 | End | 10
| Total | 22 |  | D | 10 | End | 10
| (max) |  |  | E | 10 | End | 10
| Project earliest finish: |  | 10 | F | 10 | End | 10
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.3 (ES)
SLASH BURNING EARLIEST START AND FINISH
Arc
Activity | Expected duration | Earliest start ES | Earliest finish EF | From activity | EF | To activity | ES
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 9 | 0 | 9 | Start | 0 | B | 0
B | 8 | 0 | 8 | Start | 0 | C | 0
C | 4 | 0 | 4 | Start | 0 | D | 0
D | 2 | 0 | 2 | A | 9 | E | 9
E | 2 | 9 | 11 | A | 9 | F | 9
F | 3 | 9 | 12 | B | 8 | F | 9
End | 0 | 12 | 12 | C | 4 | End | 12
| Total | 30 |  | D | 2 | End | 12
| (min) |  |  | E | 11 | End | 12
|  |  |  | F | 12 | End | 12
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.3 (LS)
SLASH BURNING LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | -1.1212e-11 | -1.1212e-11 | Start | -1.1212e-11 | A | -9.3223e-12
A | 9 | -9.3223e-12 | 9 | Start | -1.1212e-11 | B | 1
B | 8 | 1 | 9 | Start | -1.1212e-11 | C | 8
C | 4 | 8 | 12 | Start | -1.1212e-11 | D | 10
D | 2 | 10 | 12 | A | 9 | E | 10
E | 2 | 10 | 12 | A | 9 | F | 9
F | 3 | 9 | 12 | B | 9 | F | 9
End | 0 | 12 | 12 | C | 12 | End | 12
| Total | 29 |  | D | 12 | End | 12
| (max) |  |  | E | 12 | End | 12
| Project earliest finish: |  | 12 | F | 12 | End | 12
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.3 (S)
SLASH BURN PROJECT ACTIVITY SLACK
| Expected duration | Earliest |  | Latest
Activity | (days) | Start | Finish | Start | Finish | Slack
A Prepare external firebreaks | 9 | 0 | 9 | -9.3223e-12 | 9 | -9.3223e-12
B Fell internal hardwoods | 8 | 0 | 8 | 1 | 9 | 1
C Fell snags in vicinity | 4 | 0 | 4 | 8 | 12 | 8
D Check pumps and equipment | 2 | 0 | 2 | 10 | 12 | 10
E Apply chemical fire retardant | 2 | 9 | 11 | 10 | 12 | 1
F Install firing devices | 3 | 9 | 12 | 9 | 12 | 0
Key cell formulas
Cell | Formula |  |  |  | Copied to
H4 | =F4-C4 |  |  |  | H4:H9
© Buongiorno and Gilless 2002

## Prob. 12.4 (ES)
SLASH BURNING EARLIEST START AND FINISH
Arc
Activity | Expected duration | Earliest start ES | Earliest finish EF | From activity | EF | To activity | ES
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 6.1 | 0 | 6.1 | Start | 0 | B | 0
B | 8 | 0 | 8 | Start | 0 | C | 0
C | 5 | 0 | 5 | Start | 0 | D | 0
D | 2.8 | 0 | 2.8 | A | 6.1 | E | 6.1
E | 2.8 | 6.1 | 8.9 | A | 6.1 | F | 8
F | 2.6 | 8 | 10.6 | B | 8 | F | 8
End | 0 | 10.6 | 10.6 | C | 5 | End | 10.6
| Total | 24.7 |  | D | 2.8 | End | 10.6
| (min) |  |  | E | 8.9 | End | 10.6
|  |  |  | F | 10.6 | End | 10.6
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.4 (LS)
SLASH BURNING LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | 1.7646e-22 | 1.7646e-22 | Start | 1.7646e-22 | A | 1.7
A | 6.1 | 1.7 | 7.8 | Start | 1.7646e-22 | B | 1.7646e-22
B | 8 | 1.7646e-22 | 8 | Start | 1.7646e-22 | C | 5.6
C | 5 | 5.6 | 10.6 | Start | 1.7646e-22 | D | 7.8
D | 2.8 | 7.8 | 10.6 | A | 7.8 | E | 7.8
E | 2.8 | 7.8 | 10.6 | A | 7.8 | F | 8
F | 2.6 | 8 | 10.6 | B | 8 | F | 8
End | 0 | 10.6 | 10.6 | C | 10.6 | End | 10.6
| Total | 22.9 |  | D | 10.6 | End | 10.6
| (max) |  |  | E | 10.6 | End | 10.6
| Project earliest finish: |  | 10.6 | F | 10.6 | End | 10.6
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D11
C12 | =SUM(C4:C11)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G14
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J14
© Buongiorno and Gilless 2002

## Prob. 12.4 (S)
SLASH BURN PROJECT ACTIVITY SLACK
| Expected duration | Earliest |  | Latest
Activity | (days) | Start | Finish | Start | Finish | Slack
(A) Prepare external firebreaks | 6.1 | 0 | 6.1 | 1.7 | 7.8 | 1.7
(B) Fell internal hardwoods | 8 | 0 | 8 | 1.7646e-22 | 8 | 1.7646e-22
(C) Fell snags in vicinity | 5 | 0 | 5 | 5.6 | 10.6 | 5.6
(D) Check pumps and equipment | 2.8 | 0 | 2.8 | 7.8 | 10.6 | 7.8
(E) Apply chemical fire retardant | 2.8 | 6.1 | 8.9 | 7.8 | 10.6 | 1.7
(F) Install firing devices | 2.6 | 8 | 10.6 | 8 | 10.6 | 0
Key cell formulas
Cell | Formula |  |  |  | Copied to
H4 | =F4-C4 |  |  |  | H4:H9
© Buongiorno and Gilless 2002

## Prob. 12.5b
TIMBER SALE EARLIEST START AND FINISH
Arc
Activity | Expected duration | Earliest start ES | Earliest finish EF | From activity | EF | To activity | ES
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 4 | 0 | 4 | Start | 0 | B | 0
B | 3 | 0 | 3 | A | 4 | C | 4
C | 2 | 4 | 6 | A | 4 | D | 4
D | 21 | 4 | 25 | A | 4 | E | 4
E | 4 | 4 | 8 | B | 3 | C | 4
F | 5 | 25 | 30 | B | 3 | D | 4
G | 5 | 30 | 35 | B | 3 | E | 4
H | 2 | 35 | 37 | C | 6 | F | 25
I | 14 | 35 | 49 | D | 25 | F | 25
J | 5 | 37 | 42 | E | 8 | F | 25
K | 4 | 42 | 46 | F | 30 | G | 30
L | 2 | 49 | 51 | G | 35 | H | 35
M | 7 | 51 | 58 | G | 35 | I | 35
N | 2 | 58 | 60 | H | 37 | J | 37
End | 0 | 60 | 60 | J | 42 | K | 42
| Total | 434 |  | K | 46 | L | 49
| (min) |  |  | I | 49 | L | 49
|  |  |  | L | 51 | M | 51
|  |  |  | M | 58 | N | 58
|  |  |  | N | 60 | End | 60
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D19
C20 | =SUM(C4:C19)
G4 | =VLOOKUP(F4,$A$4:$D$19,4,FALSE) |  |  |  |  | G4:G24
J4 | =VLOOKUP(I4,$A$4:$C$19,3,FALSE) |  |  |  |  | J4:J24
© Buongiorno and Gilless 2002

## Prob. 12.5c
TIMBER SALE LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 4 | 0 | 4 | Start | 0 | B | 1
B | 3 | 1 | 4 | A | 4 | C | 23
C | 2 | 23 | 25 | A | 4 | D | 4
D | 21 | 4 | 25 | A | 4 | E | 21
E | 4 | 21 | 25 | B | 4 | C | 23
F | 5 | 25 | 30 | B | 4 | D | 4
G | 5 | 30 | 35 | B | 4 | E | 21
H | 2 | 38 | 40 | C | 25 | F | 25
I | 14 | 35 | 49 | D | 25 | F | 25
J | 5 | 40 | 45 | E | 25 | F | 25
K | 4 | 45 | 49 | F | 30 | G | 30
L | 2 | 49 | 51 | G | 35 | H | 38
M | 7 | 51 | 58 | G | 35 | I | 35
N | 2 | 58 | 60 | H | 40 | J | 40
End | 0 | 60 | 60 | J | 45 | K | 45
| Total | 480 |  | K | 49 | L | 49
| (max) |  |  | I | 49 | L | 49
|  |  |  | L | 51 | M | 51
|  |  |  | M | 58 | N | 58
| Project earliest finish: |  | 60 | N | 60 | End | 60
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D19
C20 | =SUM(C4:C19)
G4 | =VLOOKUP(F4,$A$4:$D$19,4,FALSE) |  |  |  |  | G4:G24
J4 | =VLOOKUP(I4,$A$4:$C$19,3,FALSE) |  |  |  |  | J4:J24
© Buongiorno and Gilless 2002

## Prob. 12.5d
TIMBER SALE PROJECT ACTIVITY SLACK
| Expected duration | Earliest |  | Latest
Activity | (days) | Start | Finish | Start | Finish | Slack
(A) Timber inventory | 4 | 0 | 4 | 0 | 4 | 0
(B) Nontimber inventory | 3 | 0 | 3 | 1 | 4 | 1
(C) Initial sale design | 2 | 4 | 6 | 23 | 25 | 19
(D) Transportation planning | 21 | 4 | 25 | 4 | 25 | 0
(E) Initial environ. assessment | 4 | 4 | 8 | 21 | 25 | 17
(F) Final environ. assessment | 5 | 25 | 30 | 25 | 30 | 0
(G) Final sale design | 5 | 30 | 35 | 30 | 35 | 0
(H) Mark sale boundaries | 2 | 35 | 37 | 38 | 40 | 3
(I) Lay out roads | 14 | 35 | 49 | 35 | 49 | 0
(J) Mark timber | 5 | 37 | 42 | 40 | 45 | 3
(K) Cruise timber | 4 | 42 | 46 | 45 | 49 | 3
(L) Prepare advertisement | 2 | 49 | 51 | 49 | 51 | 0
(M) Advertise sale | 7 | 51 | 58 | 51 | 58 | 0
(N) Award sale | 2 | 58 | 60 | 58 | 60 | 0
Key cell formulas
Cell | Formula |  |  |  | Copied to
H4 | =F4-C4 |  |  |  | H4:H17
© Buongiorno and Gilless 2002

## Prob. 12.6b
REDWOOD PARK PROJECT ACTIVITY DURATION STATISTICS
Duration (months)
Activity | Optimistic | Most likely | Pessimistic | Expected | Standard deviation
(A) Establish ranger stations | 1 | 1.5 | 2 | 1.5 | 0.16667
(B) Establish fire protection | 0.5 | 1 | 2 | 1.0833 | 0.25
(C) Purchase inholdings | 4 | 6 | 8 | 6 | 0.66667
(D) Phase out lumber operations | 9 | 11 | 13 | 11 | 0.66667
(E) Secure mineral rights | 4 | 5 | 6 | 5 | 0.33333
(F) Obtain scenic easements | 8 | 10 | 12 | 10 | 0.66667
(G) Construct signs | 3 | 4 | 6 | 4.1667 | 0.5
(H) Construct temporary campgrounds | 1 | 2 | 3 | 2 | 0.33333
(I) Designate temporary primitive campsites | 2 | 4 | 6 | 4 | 0.66667
(J) Construct temporary headquarters | 1 | 2 | 3 | 2 | 0.33333
(K) Repair existing trails | 9 | 11 | 14 | 11.1667 | 0.83333
(L) Repair boundary fences | 10 | 12 | 16 | 12.3333 | 1
(M) Post boundary | 10 | 12 | 16 | 12.3333 | 1
(N) Preliminary hydrological study | 2 | 3 | 5 | 3.1667 | 0.5
(O) Archaeological study | 4 | 6 | 8 | 6 | 0.66667
(P) Range study | 3 | 4 | 6 | 4.1667 | 0.5
(Q) Prelim environ. study | 4 | 6 | 8 | 6 | 0.66667
(R) Preliminary master plan | 3 | 5 | 7 | 5 | 0.66667
(S) Public hearings on master plan | 1 | 2 | 3 | 2 | 0.33333
(T) Final hydrological study | 1 | 2 | 3 | 2 | 0.33333
(U) Final environmental study | 3 | 4 | 5 | 4 | 0.33333
(V) Final master plan | 5 | 6 | 8 | 6.1667 | 0.5
(W) Construct new trails | 12 | 14 | 18 | 14.3333 | 1
(X) Designate permanent primitive campsites | 5 | 6 | 7 | 6 | 0.33333
(Y) Construct permanent campgrounds | 10 | 12 | 13 | 11.8333 | 0.5
(Z) Construct permanent headquarters | 10 | 12 | 14 | 12 | 0.66667
(ZZ) Construct vehicle access system | 12 | 14 | 16 | 14 | 0.66667
Key cell formulas
Cell | Formula |  |  |  | Copied to
E4 | =(B4+4*C4+D4)/6 |  |  |  | E4:E30
F4 | =(D4-B4)/6 |  |  |  | F4:F30
© Buongiorno and Gilless 2002

## Prob. 12.6c
REDWOOD PARK PROJECT EARLIEST START AND FINISH
Arc
Activity | Expected duration | Earliest start ES | Earliest finish EF | From activity | EF | To activity | ES
Start | 0 | 0 | 0 | Start | 0 | A | 0
A | 1.5 | 0 | 1.5 | A | 1.5 | B | 1.5
B | 1.0833 | 1.5 | 2.5833 | A | 1.5 | C | 1.5
C | 6 | 1.5 | 7.5 | A | 1.5 | D | 1.5
D | 11 | 1.5 | 12.5 | A | 1.5 | E | 1.5
E | 5 | 1.5 | 6.5 | A | 1.5 | F | 1.5
F | 10 | 1.5 | 11.5 | B | 2.5833 | G | 2.5833
G | 4.1667 | 2.5833 | 6.75 | B | 2.5833 | H | 2.5833
H | 2 | 2.5833 | 4.5833 | B | 2.5833 | I | 2.5833
I | 4 | 2.5833 | 6.5833 | B | 2.5833 | J | 2.5833
J | 2 | 2.5833 | 4.5833 | B | 2.5833 | K | 7.5
K | 11.1667 | 7.5 | 18.6667 | C | 7.5 | K | 7.5
L | 12.3333 | 1.5 | 13.8333 | A | 1.5 | L | 1.5
M | 12.3333 | 1.5 | 13.8333 | A | 1.5 | M | 1.5
N | 3.1667 | 1.5 | 4.6667 | A | 1.5 | N | 1.5
O | 6 | 12.5 | 18.5 | D | 12.5 | O | 12.5
P | 4.1667 | 12.5 | 16.6667 | D | 12.5 | P | 12.5
Q | 6 | 18.6667 | 24.6667 | G | 6.75 | Q | 18.6667
R | 5 | 24.6667 | 29.6667 | H | 4.5833 | Q | 18.6667
S | 2 | 29.6667 | 31.6667 | I | 6.5833 | Q | 18.6667
T | 2 | 31.6667 | 33.6667 | J | 4.5833 | Q | 18.6667
U | 4 | 31.6667 | 35.6667 | K | 18.6667 | Q | 18.6667
V | 6.1667 | 35.6667 | 41.8333 | L | 13.8333 | Q | 18.6667
W | 14.3333 | 31.6667 | 46 | N | 4.6667 | R | 24.6667
X | 6 | 31.6667 | 37.6667 | Q | 24.6667 | R | 24.6667
Y | 11.8333 | 41.8333 | 53.6667 | R | 29.6667 | S | 29.6667
Z | 12 | 41.8333 | 53.8333 | S | 31.6667 | T | 31.6667
ZZ | 14 | 41.8333 | 55.8333 | S | 31.6667 | U | 31.6667
End | 0 | 55.8333 | 55.8333 | E | 6.5 | U | 31.6667
| Total | 471.5 |  | F | 11.5 | U | 31.6667
| (min) |  |  | O | 18.5 | V | 35.6667
|  |  |  | P | 16.6667 | V | 35.6667
|  |  |  | T | 33.6667 | V | 35.6667
|  |  |  | U | 35.6667 | V | 35.6667
|  |  |  | S | 31.6667 | W | 31.6667
|  |  |  | S | 31.6667 | X | 31.6667
|  |  |  | V | 41.8333 | Y | 41.8333
|  |  |  | V | 41.8333 | Z | 41.8333
|  |  |  | V | 41.8333 | ZZ | 41.8333
|  |  |  | M | 13.8333 | End | 55.8333
|  |  |  | W | 46 | End | 55.8333
|  |  |  | X | 37.6667 | End | 55.8333
|  |  |  | Y | 53.6667 | End | 55.8333
|  |  |  | Z | 53.8333 | End | 55.8333
|  |  |  | ZZ | 55.8333 | End | 55.8333
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D32
C12 | =SUM(C4:C32)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G48
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J48
© Buongiorno and Gilless 2002

## Prob. 12.6d
REDWOOD PARK PROJECT LATEST START AND FINISH
Arc
Activity | Expected duration | Latest start LS | Latest finish LF | From activity | LF | To activity | LS
Start | 0 | -1.5526e-13 | -1.5526e-13 | Start | -1.5526e-13 | A | -1.5526e-13
A | 1.5 | -1.5526e-13 | 1.5 | A | 1.5 | B | 6.4167
B | 1.0833 | 6.4167 | 7.5 | A | 1.5 | C | 1.5
C | 6 | 1.5 | 7.5 | A | 1.5 | D | 18.6667
D | 11 | 18.6667 | 29.6667 | A | 1.5 | E | 26.6667
E | 5 | 26.6667 | 31.6667 | A | 1.5 | F | 21.6667
F | 10 | 21.6667 | 31.6667 | B | 7.5 | G | 14.5
G | 4.1667 | 14.5 | 18.6667 | B | 7.5 | H | 16.6667
H | 2 | 16.6667 | 18.6667 | B | 7.5 | I | 14.6667
I | 4 | 14.6667 | 18.6667 | B | 7.5 | J | 16.6667
J | 2 | 16.6667 | 18.6667 | B | 7.5 | K | 7.5
K | 11.1667 | 7.5 | 18.6667 | C | 7.5 | K | 7.5
L | 12.3333 | 6.3333 | 18.6667 | A | 1.5 | L | 6.3333
M | 12.3333 | 43.5 | 55.8333 | A | 1.5 | M | 43.5
N | 3.1667 | 21.5 | 24.6667 | A | 1.5 | N | 21.5
O | 6 | 29.6667 | 35.6667 | D | 29.6667 | O | 29.6667
P | 4.1667 | 31.5 | 35.6667 | D | 29.6667 | P | 31.5
Q | 6 | 18.6667 | 24.6667 | G | 18.6667 | Q | 18.6667
R | 5 | 24.6667 | 29.6667 | H | 18.6667 | Q | 18.6667
S | 2 | 29.6667 | 31.6667 | I | 18.6667 | Q | 18.6667
T | 2 | 33.6667 | 35.6667 | J | 18.6667 | Q | 18.6667
U | 4 | 31.6667 | 35.6667 | K | 18.6667 | Q | 18.6667
V | 6.1667 | 35.6667 | 41.8333 | L | 18.6667 | Q | 18.6667
W | 14.3333 | 41.5 | 55.8333 | N | 24.6667 | R | 24.6667
X | 6 | 49.8333 | 55.8333 | Q | 24.6667 | R | 24.6667
Y | 11.8333 | 44 | 55.8333 | R | 29.6667 | S | 29.6667
Z | 12 | 43.8333 | 55.8333 | S | 31.6667 | T | 33.6667
ZZ | 14 | 41.8333 | 55.8333 | S | 31.6667 | U | 31.6667
End | 0 | 55.8333 | 55.8333 | E | 31.6667 | U | 31.6667
| Total | 728.25 |  | F | 31.6667 | U | 31.6667
| (max) |  |  | O | 35.6667 | V | 35.6667
|  |  |  | P | 35.6667 | V | 35.6667
|  |  |  | T | 35.6667 | V | 35.6667
|  |  |  | U | 35.6667 | V | 35.6667
|  |  |  | S | 31.6667 | W | 41.5
|  |  |  | S | 31.6667 | X | 49.8333
|  |  |  | V | 41.8333 | Y | 44
|  |  |  | V | 41.8333 | Z | 43.8333
|  |  |  | V | 41.8333 | ZZ | 41.8333
|  |  |  | M | 55.8333 | End | 55.8333
|  |  |  | W | 55.8333 | End | 55.8333
|  |  |  | X | 55.8333 | End | 55.8333
|  |  |  | Y | 55.8333 | End | 55.8333
|  |  |  | Z | 55.8333 | End | 55.8333
| Project earliest finish: |  | 55.8333 | ZZ | 55.8333 | End | 55.8333
Key cell formulas
Cell | Formula |  |  |  |  | Copied to
D4 | =C4+B4 |  |  |  |  | D4:D31
C12 | =SUM(C4:C32)
G4 | =VLOOKUP(F4,$A$4:$D$11,4,FALSE) |  |  |  |  | G4:G48
J4 | =VLOOKUP(I4,$A$4:$C$11,3,FALSE) |  |  |  |  | J4:J48
© Buongiorno and Gilless 2002

## Prob. 12.6e
REDWOOD PARK PROJECT ACTIVITY SLACK
| Expected duration | Earliest |  | Latest |  |  |  | Critical activity
Activity | (months) | Start | Finish | Start | Finish | Slack |  | Expected duration | Standard deviation | Variance
(A) Establish ranger stations | 1.5 | 0 | 1.5 | -1.5526e-13 | 1.5 | -1.5526e-13 |  | 1.5 | 0.16667 | 0.027778
(B) Establish fire protection | 1.0833 | 1.5 | 2.5833 | 6.4167 | 7.5 | 4.9167
(C) Purchase inholdings | 6 | 1.5 | 7.5 | 1.5 | 7.5 | 4.6185e-14 |  | 6 | 0.66667 | 0.44444
(D) Phase out lumber operations | 11 | 1.5 | 12.5 | 18.6667 | 29.6667 | 17.1667
(E) Secure mineral rights | 5 | 1.5 | 6.5 | 26.6667 | 31.6667 | 25.1667
(F) Obtain scenic easements | 10 | 1.5 | 11.5 | 21.6667 | 31.6667 | 20.1667
(G) Construct signs | 4.1667 | 2.5833 | 6.75 | 14.5 | 18.6667 | 11.9167
(H) Construct temporary campgrounds | 2 | 2.5833 | 4.5833 | 16.6667 | 18.6667 | 14.0833
(I) Designate temporary primitive campsites | 4 | 2.5833 | 6.5833 | 14.6667 | 18.6667 | 12.0833
(J) Construct temporary headquarters | 2 | 2.5833 | 4.5833 | 16.6667 | 18.6667 | 14.0833
(K) Repair existing trails | 11.1667 | 7.5 | 18.6667 | 7.5 | 18.6667 | 8.2601e-14 |  | 11.1667 | 0.83333 | 0.69444
(L) Repair boundary fences | 12.3333 | 1.5 | 13.8333 | 6.3333 | 18.6667 | 4.8333
(M) Post boundary | 12.3333 | 1.5 | 13.8333 | 43.5 | 55.8333 | 42
(N) Preliminary hydrological study | 3.1667 | 1.5 | 4.6667 | 21.5 | 24.6667 | 20
(O) Archaeological study | 6 | 12.5 | 18.5 | 29.6667 | 35.6667 | 17.1667
(P) Range study | 4.1667 | 12.5 | 16.6667 | 31.5 | 35.6667 | 19
(Q) Prelim environ. study | 6 | 18.6667 | 24.6667 | 18.6667 | 24.6667 | 0 |  | 6 | 0.66667 | 0.44444
(R) Preliminary master plan | 5 | 24.6667 | 29.6667 | 24.6667 | 29.6667 | 0 |  | 5 | 0.66667 | 0.44444
(S) Public hearings on master plan | 2 | 29.6667 | 31.6667 | 29.6667 | 31.6667 | 0 |  | 2 | 0.33333 | 0.11111
(T) Final hydrological study | 2 | 31.6667 | 33.6667 | 33.6667 | 35.6667 | 2
(U) Final environmental study | 4 | 31.6667 | 35.6667 | 31.6667 | 35.6667 | 0 |  | 4 | 0.33333 | 0.11111
(V) Final master plan | 6.1667 | 35.6667 | 41.8333 | 35.6667 | 41.8333 | 0 |  | 6.1667 | 0.5 | 0.25
(W) Construct new trails | 14.3333 | 31.6667 | 46 | 41.5 | 55.8333 | 9.8333
(X) Designate permanent primitive campsites | 6 | 31.6667 | 37.6667 | 49.8333 | 55.8333 | 18.1667
(Y) Construct permanent campgrounds | 11.8333 | 41.8333 | 53.6667 | 44 | 55.8333 | 2.1667
(Z) Construct permanent headquarters | 12 | 41.8333 | 53.8333 | 43.8333 | 55.8333 | 2
(ZZ) Construct vehicle access system | 14 | 41.8333 | 55.8333 | 41.8333 | 55.8333 | 0 |  | 14 | 0.66667 | 0.44444
[7 empty] | Total | 55.8333 |  | 2.9722
Key cell formulas
Cell | Formula |  |  |  | Copied to
H4 | =F4-C4 |  |  |  | H4:H30
L4 | =K4^2 |  |  |  | L4:L30
J31 | =SUM(J4:J30) |  |  |  | L31
© Buongiorno and Gilless 2002